## Gantt Chart
OnTime				28%
Web-Engineering Seminar
Christian Wissor, Tim Mühle		Montag, 17. April 2023

							12					13					14					15					16					17					18					19					20					21					22					23					24					25					26					27					28					29					30					31					32					33					34					35					36					37
Aufgaben		Start	Dauer	Ende	% Complete	Kalendertage	Mar-23					Apr-23					May-23					Jun-23					Jul-23					Aug-23					Sep-23
		20.03.2023	61	12.06.2023	28%	85	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16
Vorbereitung		20.03.2023	21	17.04.2023	100%	29
Themenfindung		20.03.2023	10	31.03.2023	100%	12
Prototyp		03.04.2023	11	17.04.2023	100%	15
Tech-Stack bestimmen		03.04.2023	11	17.04.2023	100%	15
Prototyp entwickeln		10.04.2023	5	14.04.2023	100%	5
Präsentation (Termin 1)		10.04.2023	6	17.04.2023	100%	8

Entwicklung		18.04.2023	20	15.05.2023	0%	28
Entwicklung Basis		18.04.2023	20	15.05.2023	0%	28
Vorbereitung lokale Entwicklungsumgebung		18.04.2023	4	21.04.2023	0%	4
Datenmodell / Datenbank		18.04.2023	6	25.04.2023	0%	8
Backend		20.04.2023	18	15.05.2023	0%	26
Frontend		26.04.2023	14	15.05.2023	0%	20
Präsentation (Termin 2)		08.05.2023	6	15.05.2023	0%	8

Finalisierung		16.05.2023	20	12.06.2023	0%	28
Finalisierung		16.05.2023	20	12.06.2023	0%	28
Anpassungen		16.05.2023	9	26.05.2023	0%	11
Authentifizierung / Authorisierung		16.05.2023	19	11.06.2023	0%	27
Präsentation (Termin 3)		05.06.2023	6	12.06.2023	0%	8

Gantt Chart Template V1.1
Author: Fernando Ribeiro <pinguim.ribeiro@gmail.com>

How To Use
INSERT LINES:
Insert the required number of lines: click the line number and drag down
From the template, copy the required section or just one line
INPUT DATA:
WBS: to itemize the WBS copy and past the required level from the template
Enter a Task and Resource Names
Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.

	Holidays
	1/1/14
	3/4/14
	4/18/14
	4/20/14
	4/25/14
	5/1/14
	6/10/14
	8/15/14
	12/8/14
	12/25/14